## Лист1
№ | Код работы (расчет) | Расчет ресурсов | Type of data | Work group | Type of work | Code of work | Name of work type | Discharge of workers | Unit of measurement | Time norm per unit of volume, hour | Labor intensity |  | Of machinery and mechanisms, mach-hour | Note
[6 empty] | Resource code | Resource name |  | Resource group | Amount | Workers, per-hour | Machinists, per-hour
1 |  |  | Structure | 02. Earthwork |  | W.02 | 02. Earthwork
2 |  |  | Structure | 02.01. Preparation of construction site (line) |  | W.02.01 | Preparation of construction site (line)
3 | M.02.01.01 |  | Type of work | 02.01. Preparation of construction site (line) | 02.01.01. Расчистка от лесорастительности | W.02.01.01 | Clearing from forest plantation |  | m2 | 0.003 | 0.012 | 0.009 | 0.015
4 | M.02.01.02 |  | Type of work | 02.01. Preparation of construction site (line) | 02.01.02. Срезка плодородного слоя с перемещением в отвал до 100м | W.02.01.02 | Cutting the fertile layer and moving it to the pile to 100m |  | m3 | 0.035 | 0 | 0.035 | 0.035
5 |  |  | Structure | 02.02. Territory planning |  | W.02.02 | Territory planning
6 | M.02.02.04 |  | Type of work | 02.02. Territory planning | 02.02.01. Fill construction (with multilayer consolidation by vibrating rollers) | W.02.02.01 | Fill construction (with multilayer consolidation by vibrating rollers) |  | m3 | 0.03 | 0.015 | 0.06 | 0.06
7 | M.02.02.04 | M.02.02.04Ресурсы (Рабочие) | Resources (Workers) | 02.02. Territory planning | 02.02.01. Fill construction (with multilayer consolidation by vibrating rollers) | Wor.09.02.02 | Ancillary worker | 2 | Workers | 0.5 | 0.015
8 | M.02.02.04 | M.02.02.04Ресурсы (Машинисты) | Resources (Machine operators) | 02.02. Territory planning | 02.02.01. Fill construction (with multilayer consolidation by vibrating rollers) | Meh.06.03.05 | Road roller driver | 5 | Machine operators | 0.5 |  | 0.015
10 | M.02.02.04 | M.02.02.04Ресурсы (Машинисты) | Resources (Machine operators) | 02.02. Territory planning | 02.02.01. Fill construction (with multilayer consolidation by vibrating rollers) | Meh.02.01.06 | The bulldozer driver | 6 | Machine operators | 1 |  | 0.03
11 | M.02.02.04 | M.02.02.04Ресурсы (Машинисты) | Resources (Machine operators) | 02.02. Territory planning | 02.02.01. Fill construction (with multilayer consolidation by vibrating rollers) | Meh.01.01.05 | Driver | 5 | Machine operators | 0.5 |  | 0.015
12 | M.02.02.04 | M.02.02.04Ресурсы (Машины и механизмы) | Resources (Machinery and mechanisms) | 02.02. Territory planning | 02.02.01. Fill construction (with multilayer consolidation by vibrating rollers) | Mac.01.08.02 | Road roller |  | Machinery and mechanisms | 0.5 |  |  | 0.015
14 | M.02.02.04 | M.02.02.04Ресурсы (Машины и механизмы) | Resources (Machinery and mechanisms) | 02.02. Territory planning | 02.02.01. Fill construction (with multilayer consolidation by vibrating rollers) | Mac.01.01.03 | Bulldozers with engine power up to 180 kW |  | Machinery and mechanisms | 1 |  |  | 0.03
15 | M.02.02.04 | M.02.02.04Ресурсы (Машины и механизмы) | Resources (Machinery and mechanisms) | 02.02. Territory planning | 02.02.01. Fill construction (with multilayer consolidation by vibrating rollers) | Mac.02.04.07 | Tank car |  | Machinery and mechanisms | 0.5 |  |  | 0.015
16 | M.02.02.05 |  | Type of work | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | W.02.02.02 | Vertical planning of areas, slopes, canals and excavations |  | m2 | 0.083 | 0.166 | 0.083 | 0.083
17 | M.02.02.05 | M.02.02.05Ресурсы (Рабочие) | Resources (Workers) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Wor.01.05.04 | Road worker | 4 | Workers
18 | M.02.02.05 | M.02.02.05Ресурсы (Рабочие) | Resources (Workers) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Wor.09.02.02 | Ancillary worker | 2 | Workers | 2 | 0.166
19 | M.02.02.05 | M.02.02.05Ресурсы (Машинисты) | Resources (Machine operators) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Meh.02.01.06 | The bulldozer driver | 6 | Machine operators
20 | M.02.02.05 | M.02.02.05Ресурсы (Машинисты) | Resources (Machine operators) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Meh.06.01.05 | Grader driver | 5 | Machine operators
21 | M.02.02.05 | M.02.02.05Ресурсы (Машинисты) | Resources (Machine operators) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Mac.04.01.05 | Excavator driver | 5 | Machine operators | 1 |  | 0.083
22 | M.02.02.05 | M.02.02.05Ресурсы (Машины и механизмы) | Resources (Machinery and mechanisms) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Mac.01.01.03 | Bulldozers with engine power up to 180 kW |  | Machinery and mechanisms
23 | M.02.02.05 | M.02.02.05Ресурсы (Машины и механизмы) | Resources (Machinery and mechanisms) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Mac.01.01.02 | Bulldozer with engine power from 180 kW to 240 kW |  | Machinery and mechanisms
24 | M.02.02.05 | M.02.02.05Ресурсы (Машины и механизмы) | Resources (Machinery and mechanisms) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Mac.01.08.01 | Grader |  | Machinery and mechanisms
25 | M.02.02.05 | M.02.02.05Ресурсы (Машины и механизмы) | Resources (Machinery and mechanisms) | 02.02. Territory planning | 02.02.02. Vertical planning of areas, slopes, canals and excavations | Mac.01.03.02 | Excavator with a bucket capacity of 1.0-1.4 m3 |  | Machinery and mechanisms | 1 |  |  | 0.083
26 | M.02.02.06 |  | Type of work | 02.02. Territory planning | 02.02.03. Vertical planning of areas, slopes, canals and embankments by hand | W.02.02.03 | Vertical planning of areas, slopes, canals and embankments by hand |  | m2 | 0.05 | 0.05 | 0 | 0
27 | M.02.02.06 | M.02.02.06Ресурсы (Рабочие) | Resources (Workers) | 02.02. Territory planning | 02.02.03. Vertical planning of areas, slopes, canals and embankments by hand | Wor.01.05.04 | Road worker | 4 | Workers | 1 | 0.05